## Sheet1
Week | Task | Est. Hours | Deadline
Week 1: June 2 – June 8 | Create Evaluation Form | 5 | June 6
Week 1: June 2 – June 8 | Edit Evaluation Form | 4 | June 7
Week 1: June 2 – June 8 | Delete Evaluation Form | 3 | June 8
Week 1: June 2 – June 8 | View Form Details | 3 | June 8
Week 2: June 9 – June 15 | Docker Implementation (Frontend containerization) | 5 | June 11
Week 2: June 9 – June 15 | Polish/Create UI Validation | 2 | June 12
Week 2: June 9 – June 15 | Test full FE flows manually | 3 | June 14
Week 2: June 9 – June 15 | Buffer or wrap-up | 5 | June 15
Week 3: June 16 – June 22 | CI/CD Setup for Backend (GitHub Actions or similar) | 6 | June 19
Week 3: June 16 – June 22 | Pipeline Configs (build/test/lint steps) | 5 | June 21
Week 3: June 16 – June 22 | Docker Compose setup with backend | 4 | June 22
Week 4: June 23 – June 29 | Write Remaining Domain Unit Tests | 5 | June 25
Week 4: June 23 – June 29 | Create Generic Test Class for Handlers | 5 | June 27
Week 4: June 23 – June 29 | Unit Test All Handlers Using Generic Class | 5 | June 29
June 30 – July 1 | Integration Test Setup (Startup + Docker Integration) | 6 | July 1
June 30 – July 1 | Final Testing / Documentation | 3 | July 1